## Sheet1
FEATURE	EXPECTED TIME (h)	ACTUAL TIME (h)	date of completion

PERSISTENCY	12	0
save settings (shared preferences)	5
save ebooks (how? not sure yet exactly)	5
save current position in each book	2

SERVICES	94	0
local library to manage books/texts	5
settings (language, ui,...)	5
add/delete books (must work with all formats)	8
play/pause/skip chapter and sound	8
text to speech integration	10
word tracker (which word is read right now)	8
download books from web library (proj. gutenberg)	15
search in books (words)/library(books)/web(books)	10
multiple formats support (pdf, txt, epub, mobi, html)	20
display "currently playing..." in status bar	5

UI	38	21
ui design	8	6	09.07.14
ui generation (+multiple resolutions)	10	10	09.07.14
ui implementation	15	5	todo
i18n (english+german+?)	5

TESTING	15	0
tests with multiple user devices	15

RESEARCH	7	4
topic research	2	2	03.07.14
libs	2
ui	1	2	04.07.14
persistency	2

SUM	166	25