## Sheet1
FEATURE	EXPECTED TIME (h)	ACTUAL TIME (h)	date of completion

PERSISTENCY	12
save settings (shared preferences)	5
save ebooks (how? not sure yet exactly)	5
save current position in each book	2

SERVICES	83
local library to manage books/texts	5
settings (language, ui,...)	5
add/delete books	4
play/pause/skip chapter and sound	8
text to speech integration	8
word tracker (which word is read right now)	8
download books from web library (proj. gutenberg)	15
search in books (words)/library(books)/web(books)	10
multiple formats support (pdf, txt, epub, mobi, html)	20

UI	38
ui design	8
ui generation (+multiple resolutions)	10
ui implementation	15
i18n (english+german+?)	5

TESTING	15
tests with multiple user devices	15

RESEARCH	7
topic research	2	2	03.07.14
libs	2
ui	1
persistency	2

SUM	155