## Sheet1
FEATURE	EXPECTED TIME (h)	ACTUAL TIME (h)	date of completion

PERSISTENCY	12	9,5
save settings (shared preferences)	5	1	13.07.14
save ebooks (how? not sure yet exactly)	5	7	22.08.14
save current position in each book	2	1,5	17.07.14

SERVICES	94	84
local library to manage books/texts	5	5	24.08.14
settings (language, ui,...)	5	5	25.08.14
add/delete books (universal storing)	8	5	15.07.14
play/pause/skip chapter and sound	8	12,5	25.08.14
text to speech integration	10	7	31.07.14
sentence tracker(+scrolling and picking of sentence)	8	13,5	17.08.14
download books from web library (proj. gutenberg)	15	3
search books/chapters	10	5,5	13.08.14
multiple formats support (pdf, txt, epub, html)	20	14	29.08.14
Background playing and notification bar	5	13,5	25.08.14

UI	38	53
ui design	8	6	09.07.14
ui generation (+multiple resolutions)	10	10	09.07.14
ui implementation	15	35	08.09.14
i18n (english+german+?)	5	2	11.09.14

TESTING	15	7
tests with multiple user devices	15	7	todo

RESEARCH	7	18
topic research	2	3	29.08.14
libs	2	9	29.08.14
ui	1	2	04.07.14
persistency	2	4	15.07.14

SUM	166	171,5	03.07.2014-todo