## Sheet1
FEATURE	EXPECTED TIME (h)	ACTUAL TIME (h)	date of completion

PERSISTENCY	12	8,5
save settings (shared preferences)	5	0,5	13.07.14
save ebooks (how? not sure yet exactly)	5	6,5	03.08.14
save current position in each book	2	1,5	17.07.14

SERVICES	94	67,5
local library to manage books/texts	5	4	17.07.14
settings (language, ui,...)	5	4	todo
add/delete books (universal storing)	8	5	15.07.14
play/pause/skip chapter and sound	8	11	todo
text to speech integration	10	7	31.07.14
sentence tracker(+scrolling and picking of sentence)	8	13,5	17.08.14
download books from web library (proj. gutenberg)	15	2	todo
search books/chapters	10	5	13.08.14
multiple formats support (pdf, txt, epub, mobi, html)	20	5	todo
Background playing and notification bar	5	11	todo

UI	38	44
ui design	8	6	09.07.14
ui generation (+multiple resolutions)	10	10	09.07.14
ui implementation	15	27	todo
i18n (english+german+?)	5	1	todo

TESTING	15	3
tests with multiple user devices	15	3	todo

RESEARCH	7	17
topic research	2	3	todo
libs	2	8	todo
ui	1	2	04.07.14
persistency	2	4	15.07.14

SUM	166	140	03.07.2014-todo