## Sheet1
FEATURE	EXPECTED TIME (h)	ACTUAL TIME (h)	date of completion

PERSISTENCY	12	8,5
save settings (shared preferences)	5	0,5	13.07.14
save ebooks (how? not sure yet exactly)	5	6,5	03.08.14
save current position in each book	2	1,5	17.07.14

SERVICES	94	56,5
local library to manage books/texts	5	4	17.07.14
settings (language, ui,...)	5	3	todo
add/delete books (universal storing)	8	5	15.07.14
play/pause/skip chapter and sound	8	10	todo
text to speech integration	10	7	31.07.14
sentence tracker	8	8	todo
download books from web library (proj. gutenberg)	15	2	todo
search in books/chapters/server	10	4,5	todo
multiple formats support (pdf, txt, epub, mobi, html)	20	2	todo
Background playing and notification bar	5	11	28.07.14

UI	38	43
ui design	8	6	09.07.14
ui generation (+multiple resolutions)	10	10	09.07.14
ui implementation	15	26	todo
i18n (english+german+?)	5	1	todo

TESTING	15	2
tests with multiple user devices	15	2	todo

RESEARCH	7	15
topic research	2	2	03.07.14
libs	2	7	todo
ui	1	2	04.07.14
persistency	2	4	15.07.14

SUM	166	125	03.07.2014-todo